## Costs
GOAL: We would like to avoid special assessments.
To achieve this we need to plan our finances not just for the next five years; but with the life cycle of all the parts of the building in mind (50 year plan)
This way we can understand the costs that need to come out of the reserves now and in the future
ALL FIGURES ARE ESTIMATES AND BEST GUESSES
EXPENSES | 5 Year Plan
Expected projects in the next five year | Cost of projects
Masonry Phase II | 320000
Roofs | 180000 | 7 roofs to go. Cost $25K each in 2012
Smoke Alarm System | 120000
Rental Unit Refurb | 5000
2nd Rental Unit Repair | 5000
Plumbing | 22000
Misc | 56000
Total expenses from reserves over the next five years | 708000 | line 16
catastophe predictons
| 2013 | 2014 | 2015 | 2016 | 2017 |  |  | 1 year | 2 year | 3 year | 4 year
Budget for operating expenses | 239285 | 246463.55 | 253857.4565 | 261473.1802 | 269317.3756 |  |  | 947285 | 1193748.55 | 1447606.0065 | 1709079.1867
Total operating expenses for next five years (3% inflation) | 1270396.5623 | line 20 | [5 empty] | short
[7 empty] | 0% | 541343 | 381864.55 | 229780.0065 | 85311.1867
Total needed for repairs (from reserves) over the next five years | 708000 | from line 16 |  |  |  |  | 3% | 531564.74 | 362308.03 | 200445.2265 | 46198.1467
Total operating cost for next five years (3% inflation) | 1279502 | from line 20
Total Income needed in next five years | 1978396.5623
INCOME | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL
Current Yearly Condo Fees No Increase | 325942 | 325942 | 325942 | 325942 | 325942 | 1629710 |  | 405942 | 811884 | 1217826 | 1623768
Current Yearly Condo Fees 3% increase | 335720.26 | 335720.26 | 335720.26 | 335720.26 | 335720.26 | 1678601.3 |  | 415720.26 | 831440.52 | 1247160.78 | 1662881.04
Other Sources | 80000 | 80000 | 80000 | 80000 | 80000 | 400000
| 0 increase | 3% increase
TOTAL INCOME | 2029710 | 2078601.3 |  | line 34
Target Reserve for 2018
Base | 125000 | This number can be reduced to zero once we are in phase with the 50 year plan
50 year plan (see Long Term Yearly Costs sheet) | 163000 | Masonry Round III makes this something tht we don't want to delay getting started on
Total Target for 2018 | 288000
ASSETS
Current Amount in Reserves | 233000
Project Reserves
| 0 increase | 3% increase
Income | 2029710 | 2078601.3 |  | from line 34
Assests | 233000 | 233000 |  | from line 43
Total Income + Assests | 2262710 | 2311601.3 |  | total
Expenses | 1978396.5623 | 1978396.5623 |  | from line 24
Reserve target | 293000 | 293000 |  | from line 40
Total money needed | 2271396.5623 | 2271396.5623 |  | total
Project Reserves for 2018
Projected | 279313.4377 | 328204.7377 |  | line 51 - line 55
Variance from Target | -8686.5623 | 40204.7377
*We will not be liquid even if we hit all our 5 year costs early
Masonry:
The masonry is old. We have completed phase 1 of replacing the old masonry.
It is expected that Phase II will need to take place in the next 3-5 years.
We have currently replaced many of the lintels and the top 6 feet have been repointed/replaced.
All lintels and masonry will probably need to be replaced in the next 20 years
Roofs:
All of our roofs are past their expected lifetime. Some are extremely past their lifetimes.
5 roofs were replaced this last year.
We have 7 more roofs to go.
Painting:
Good for ~7-10 years
Rental Refurbishing:
Good for ~5-10 years
Plumbing:
Our plumbing is old.
This is an estimate based on costs that have arisen in the past and what we expect will need to be repaired.
Basement ceiling:
Good for forseeable future
Smoke Alarm:
The system will need to be replaced within five years
Misc:
Our budget usually estimates $20K/ year in miscellaneous fees
We are lowering this to $10K/year due to improved itemization

## Long Term Yearly Costs
EXPENSES | Long Term Yearly Reserve Expenditures | 50 year plan for next five years (because we have not finished need repair and the repairs are covered in the 5 year plan
Expected projects in the next five year | Cost of projects
Masonry | 24000 | 12000
Roofs | 14000 | 5833.3333
Back stairwell painting | 3333.3333 | 3333.3333
Smoke Alarm System | 75 | 0 | dealt with in five year plan up fron
Rental Unit Refurbishing | 2000 | 0 | dealt with in five year plan up fron
Plumbing | 4000 | 0 | dealt with in five year plan up fron
Outside Painting | 5000 | 5000
Heating Repairs | 1000 | 1000
Misc | 15000 | 0 | dealt with in five year plan up fron
Total expenses from reserves over the next five years | 68408.3333 | 27166.6667

## catastrophic failure
catastophe predictons
COST |  | 1 year | 2 year | 3 year | 4 year
all project are needed |  | 947285 | 1193749 | 1447606 | 1709079
INCOME
income model 1 |  | 405942 | 811884 | 1217826 | 1623768
income model 2 |  | 415720.26 | 831440.52 | 1247160.78 | 1662881.04
SHORTFALL
income model 1 | 0% | 541343 | 381864.55 | 229780.01 | 85311.19
income model 2 | 3% | 531564.74 | 362308.03 | 200445.23 | 46198.15